## 90 day plan
90 Day Plan | [5 empty] | Client Time Commitment
MILESTONE | TASKS & OBJECTIVES | OWNER | STAKEHOLDERS | TIMEFRAME | Timeline (option 2)
Kickoff | [5 empty] | Total: 2
| Kickoff Meeting (virtual) | Responsive: Onboarding Consultant | Client: Core Admins, SMEs, Exec Sponsor | Day 1 to 15 | Weeks 1 + 2 | 1
| Historical Documentation (provide historical Q&A pairs, unanswered RFx) | [clientname]: Core Admins | Responsive: Onboarding Consultant |  |  | 1
| Schedule all Onboarding Sessions + Implementation Workshop | Responsive: Onboarding Consultant | Client: Core Admins, SMEs, Exec Sponsor |  |  | 0.5
| Customer login and access Responsive Academy | [clientname]: Core Admins | Responsive: Onboarding Consultant |  |  | 0.5
Customer Work & Responsibilities | [5 empty] | Total:20
| Review Integration documentation | [clientname]: IT Team | Responsive: Onboarding Consultant | Day 15 to 45 | Weeks 3, 4, 5, 6 | 0.5
| Customer to set up all integrations + SSO | [clientname]: IT Team | Responsive: Onboarding Consultant |  |  | 1
| Client testing for integrations + SSO | [clientname]: IT Team | Responsive: Onboarding Consultant |  |  | 0.5
| Provide historical Q&A pairs, sample RFx | [clientname]: Core Admins | Responsive: Onboarding Consultant |  |  | 1
| Review Help Center articles (Content Library, Content Mangament, Project Lifecycle) | [clientname]: Core Admins | Responsive: Onboarding Consultant |  |  | 1
| Attend all Onboarding training sessions x 4 | [clientname]: Core Admins | Responsive: Onboarding Consultant |  |  | 4.5
| Content and data migration completed | [clientname]: Core Admins, SMEs | Responsive: Onboarding Consultant |  |  | 5
| Content Library setup & organization completed | [clientname]: Core Admins, SMEs | Responsive: Onboarding Consultant |  |  | 5
| Confirm user access, login, and set launch date | [clientname]: IT Team | Responsive: Onboarding Consultant |  |  | 1
| Verify whitelist status for Resopnsive domain | [clientname]: IT Team | Responsive: Onboarding Consultant |  |  | 0.5
Onboarding Training Sessions | [5 empty] | Total: 4.5
| Content Library Basics (virtual training session) | Responsive: Onboarding Consultant | Client: Core Admins | Day 15 to 45 | Weeks 3, 4, 5, 6 | 1
| Content Management (virtual training session) | Responsive: Onboarding Consultant | Client: Core Admins |  |  | 1
| Project Lifecylce Management (virtual training session) | Responsive: Onboarding Consultant | Client: Core Admins |  |  | 1.5
| Flex Session (virtual training sessions) | Responsive: Onboarding Consultant | Client: Core Admins |  |  | 1
Go-Live Readiness (Client Side) | [5 empty] | Total: 4
| Confirm integrations are setup in production environment | [clientname]: IT Team | Responsive: Onboarding Consultant | Day 45 - 60 | Weeks 7, 8 | 1
| Deployment plan, project workflow, and go-live checklist (+ confirm launch date) | [clientname]: Core Admins, IT Team | Responsive: Onboarding Consultant
| Confirm customer login and access Responsive Academy | [clientname]: Core Admins | Responsive: CSM |  |  | 0.5
Launch and Adoption | [5 empty] | Total: 17
| Official Go-Live: rollout Responsive to all internal users | [clientname]: Core Admins | Responsive: CSM | Day 60 to 90 | Weeks 9, 10, 11, 12 | 4
| Schedule and deliver role-specific training to all end users and SMEs | [clientname]: Core Admins | Responsive: CSM |  |  | 8
| Super Admin meets with Customer Success Manager | [clientname]: Core Admins | Responsive: CSM |  |  | 1
| Verify all end-users complete their required tasks within Responsive | [clientname]: Core Admins | Responsive: CSM |  |  | 4
Overal Total: 47.5

## 1. Onboarding Resources Tasks
STATUS | TASKS & OBJECTIVES | OWNER | CLIENT TASKS | RESOURCES | NOTES/QUESTIONS
Kickoff
| Kickoff Meeting (virtual) | Responsive: Onboarding Consultant
| Historical Documentation (provide historical Q&A pairs, unanswered RFx) | [clientname]: Core Admins | Prepare sample documents for Onboarding Train-the-Trainer Sessions: 1) Historical Data - content containing completed Historical Content and/or Question & Answer pairs; usually a past RFP with completed responses (docx or xlsx preferred). 2) Blank Questionnaire/Project - a blank RFP, RFI, or Questionnaire; usually an unanswered project (docx or xlsx preferred). 3) Word Template - if your team uses a branded Word document for your final submissions (docx required). Only needed to provide if this is applicable to your projects. | Help Center: Prep Content for Import
| Schedule all Onboarding Sessions + Implementation Workshop | Responsive: Onboarding Consultant
| Customer login and access Responsive Academy | [clientname]: Core Admins
Customer Work & Responsibilities
| Review Integration documentation | [clientname]: IT Team
| Customer to set up all integrations + SSO | [clientname]: IT Team | Check with your IT if any additional set up is needed to navigate to Responsive in your web browser. (i.e. Ability to access your instance, ability to upload documents to Responsive, ability to downloaded documents from Responsive). Responsive supports most standard browsers. (Chrome is the recommended browser.) Responsive can send system notifications to your email, i.e. assignment notifications, task reminders, newsletters, marketing communications, etc. | Responsive App URL
| Client testing for integrations + SSO | [clientname]: IT Team | Refer to the Kickoff deck to see available Integrations and Add-ons included in your package. Add your IT Admins as Admin Users in Responsive. Coordinate with your IT to schedule configurations. | Help Center: Integrations
| Provide historical Q&A pairs, sample RFx | [clientname]: Core Admins | Prepare sample documents for Onboarding Train-the-Trainer Sessions: 1) Historical Data - content containing completed Historical Content and/or Question & Answer pairs; usually a past RFP with completed responses (docx or xlsx preferred). 2) Blank Questionnaire/Project - a blank RFP, RFI, or Questionnaire; usually an unanswered project (docx or xlsx preferred). 3) Word Template - if your team uses a branded Word document for your final submissions (docx required). Only needed to provide if this is applicable to your projects.
| Review Help Center articles (Content Library, Content Mangament, Project Lifecycle) | [clientname]: Core Admins | Core Admin Team to meet internally to discuss content organization structure. Leverage the "Content Organization - Worksheet (Excel)" to begin planning your content strategy. | Download: Content Organization - Worksheet (Excel)
|  |  | Core Admin Team to meet internally to discuss project management strategy. Leverage the "Project Workflow - Worksheet (Excel)" to begin planning your project workflow. | Download: Project Workflow - Worksheet (Excel)
|  |  | Run test projects in Responsive to solidify workflow. | Help Center: Projects Training Slides (new UX)
| Attend all Onboarding training sessions | [clientname]: Core Admins
| Content and data migration completed | [clientname]: Core Admins, SMEs
| Content Library setup & organization completed | [clientname]: Core Admins, SMEs
| Confirm user access, login, and set launch date | [clientname]: IT Team | Define Super Admin and Core Admin Team - responsible for Responsive implementation and championing internal rollout of Responsive. | Refer to Kickoff information
|  |  | Super Admin / Core Admin Team to review Organization Settings and User Management. | Academy: Administration
| Verify whitelist status for Resopnsive domain | [clientname]: IT Team
Onboarding Training Sessions
| Content Library Basics (virtual training session) | Responsive: Onboarding Consultant | Required pre-work: Send any required sample documents to your Onboarding Consultant. | Academy: Foundations of Content Management
| Content Management (virtual training session) | Responsive: Onboarding Consultant | Required pre-work: Complete the Content Management Learning Path in Responsive Academy.
| Project Lifecylce Management (virtual training session) | Responsive: Onboarding Consultant | Required pre-work: Send any required sample documents to your Onboarding Consultant. Required post work: Complete the Project Management Learning Path in Responsive Academy | Academy: Foundations of Project Management
| Flex Session (virtual training sessions) | Responsive: Onboarding Consultant | To be deteremind by client and onboarding consultant
Implementation Workshop & Readiness
| Confirm integrations are setup in production environment | [clientname]: IT Team | Reach out to Responsive Support team if Technical Assistance is required. | Contact Support
| Strategic Implementation Worshop (virtual session) | Responsive: Onboarding Consultant & CSM | Required pre-work: 1) Be prepared to talk about your Content Organization structure and Project Workflow. 2) Send any questions to Onboarding Consultant prior to meeting. | Responsive Live: Let's Talk Implementation
| Deployment plan, project workflow, and go-live checklist (+ confirm launch date) | [clientname]: Core Admins, IT Team
| Confirm customer login and access Responsive Academy | [clientname]: Core Admins
| Establish recurring meeting cadence with CSM for Launch & Adoption window | Responsive: CSM | Office Hours are provided to the Core Admin Team as recurring scheduled meeting times with CSM. Office Hours can be used to address general questions around the tool, as well as covering additional best practices. These sessions are highly recommended during the first 3 months of implementation. | Schedule meeting times with CSM
Launch and Adoption
| Official Go-Live: rollout Responsive to all internal users | [clientname]: Core Admins | Leverage the pre-made PowerPoint deck in our Help Center to create your own internal training slides for your end-users. Soft-launch or full Go-live within your organization. Pilot a project, or begin running live projects in Responsive. We encourage listening in to our past Webinar to inspire some ideas: - Evaluate your current process for improvement. - Adhere to APMP best practices by taking advantage of more Responsive features. - Evaluate how Responsive can help teams from proposals, sales, presales, customer support, and IT improve responses and content over time. | Help Center: Train the Trainer PPT Deck
| Schedule and deliver role-specific training to all end users and SMEs | [clientname]: Core Admins
| Super Admin meets with Customer Success Manager | [clientname]: Core Admins
| Verify all end-users complete their required tasks within Responsive | [clientname]: Core Admins

## 2. Additional Resources
Training Resources
| Moderation | Complete the Moderation course in Responsive Academy. Core Admin Team to discuss internally whether Moderation will be needed. Speak with your Onboarding Consultant on this topic. | Academy: Moderation
| Document Library | Begin uploading documents into the Document Library (as needed). | Help Center: Managing the Document Library
| Intake | Complete the Intake course in Responsive Academy. Core Admin Team to discuss internally whether Moderation will be needed. Speak with your Onboarding Consultant on this topic. | Academy: Enabling and Managing Intake
| Standard Reporting | Review the Standard Reporting available in the application. | Help Center: Reporting in Responsive
| Section Templates | Complete Section Templates module in Responsive Academy, including Section Template creation, organization, and usage. | Academy: Introduction to Section Templates
| Response Templates | Review Response Templates resources. | Responsive Live: Let's Talk Response Templates
| Add Section Templates & Response Templates into Responsive | Upload Response Templates and Section Templates into Responsive (as needed). | Help Center: Response Templates
| Responsive Academy and Help Center | Check out our Responsive Academy for available courses. Browse the Help Center for additional resources. | Responsive Academy
| Stay in the know! | In the Help Center, check out the Release Notes and Best Practices pages for all the latest about Responsive. Be sure to sign up for our newsletters to stay up to date on Responsive news, events, and announcements. Reach out to your CSM if you are not sure how to subscribe. | Product Release Notes
Webinar: Scale your response management process
Additional Support Resources
| Meeting: Introduction to Account Manager - Account Review | Account Reviews are scheduled strategic meetings between the Customer and Responsive. The CSM will introduce the Responsive Account Manager, review progress toward goals, share any important release updates or valuable new features, and evaluate any gaps or additional needs. The Core Admin Team will join in this meeting, but it is encouraged to invite Responsive Champions and Executive Sponsors as well. | CSM will coordinate this meeting
| Professional Services for your Additional Needs | If your team requires additional support and training throughout onboarding, our Professional Services team can offer implementation services. Ask your Onboarding Consultant or Customer Success Manager for more information. | Datasheet of Professional Services can be provided upon request

## 3. Integrations Resources
Integration | Linked Resources | Owner | Internal Resource | Status | Targeted for Week of | Date of Completion | Assigned To | Client Notes
(If applicable) See Integration Guides from the Help Center. Add your IT Admins as Admin Users in Responsive. Coordinate with your IT to configure integrations.
CRM - Salesforce
| Salesforce Integration Hub (Lightning) | Client
| Salesforce Integration Hub (Classic) | Client
SSO Connector (TBD)
| Okta SAML Configuration | Client
| Generic SAML Configuration | Client
Cloud Storage Connector (Sharepoint and Google Drive)
| Sharepoint Integration Manual | Client
Google Drive
Responsive Lookup
| Getting Started with Responsive Lookup | Client
Responsive LookUp for MS Teams
JIRA
| JIRA Integration | Client
Mulit-language User Interface
| Changing the display language | Client
Custom Reports
| Working with custom reports | Client
| Creating Top Custom Reports | Client
Custom Roles
| Creating Custom Roles | Client
| Custom Role Permissions | Client
Autograph
| Autograph Overview | Client
API
| API Documentation | Client

## 4. Content Organization Plan
Use this worksheet to begin making sense of your content and setting a foundation for your organization structure.
Recommended resources: Need Definitive access: | Organizing your Answer Library Content
Tags | General categorization across content
Name | Group | Governance
Collections | Segmentation of content; plus restrictions on visibility per user
Name | Needs restrictions on visibility?
Custom Fields | Unique categorization structure
Name | Specific values (if applicable) | Type | Group
Response headers | Notes | Guidance
Response 1 |  | Uppercase/lowercase usage
Response 2
Response 3
Response - Short
Response - Brief | Same content as short but builds
Response - Long | Same content as brief but builds | Question nomenclature
Response - Long with Graphics | Same content as long but builds | If using RFP questions, remove filler words like describe, please, if any, etc.
Response - Long without Graphics | Same content as long with graphics but builds | Adopt naming convention standard for record tags.

## 5. Content Reference Tags
Content Reference Tags
Merge tag name | Meaning/definition | Group name | Column1 | Notes

## 6. Project Workflow Plan
Project Workflow Plan
Use this worksheet to begin planning what your Project Workflow will look like in RFPIO.
| Project Creation | Will you require an Intake process?
|  |  | Project Requester (only for Intake) | Teams or specific users who will be responsible | Notes about your workflow in this process
|  |  | example | Sales team | Submit request and project docs via SF
Who will be creating projects in RFPIO?
Who will be owning projects in RFPIO? --> Project Primary Contact
|  |  | Project Primary Contact | Teams or specific users who will be responsible | Notes about your workflow in this process
|  |  | example | Proposal Managers | For Intake Only - Review request via RFPIO Intake, and Approve/Reject project
|  |  |  | Proposal Managers | Will create projects, manage assignments, and own project completion
|  |  |  | Sales Rep | Will be additional Primary Contact for backup and for visibility
| Collaboration | Who will be responding to questions in RFPIO? --> Authors
Which User Roles will you set for your team?
Will you require Guest User Functionality? --> Guest
|  |  | Authors and Guest Users (if applicable) | Teams or specific users who will be responsible | Notes about your workflow in this process
|  |  | example | Proposal Team | Will provide responses to questions / requirements
Proposal Team will be set up with Team Member access in RFPIO
All users will have RFPIO access; no Guest users needed
Who will be reviewing responses in RFPIO? --> Reviewers
|  |  | Authors and Guest Users (if applicable) | Teams or specific users who will be responsible | Notes about your workflow in this process
|  |  | example | Product Owners | Will review responses that were applied manually (Answer Library was not Used or Edited)
|  |  |  | Marketing Team | Will review final responses and mark Sections as Complete
| Project Management | Will you need to customize your Project Types and Project Stages?
What will be your default for the Save In Answer Library setting?
|  |  | Project Organization Settings | Item | Notes
|  |  | example | Project Types | - No change; same as out-of-box defaults - Reach out to Core Admin Team or Super Admin for any changes
|  |  |  | Project Stages | - No change; same as out-of-box defaults - Reach out to Core Admin Team or Super Admin for any changes
|  |  |  | Save In Answer Library Default | - Default will be set as Disabled - This setting will not be adjusted in the instance-level, but will be adjusted on a Project-level as needed
What is your Active Project Limit?
Define Active Projects Categories: Current, Completed, Canceled, Trash
When should a project be Archived?
|  |  | Active Projects vs. Archived | Item | Notes
|  |  | example | Project Limit | (?) concurrent projects - check contract or ask Account Manager
|  |  |  | Current | Project is new and in progress
|  |  |  | Completed | Project has been completed and submitted
|  |  |  | Canceled | Project has been canceled
|  |  |  | Trash | Projects in Trash are set up to be permanently deleted after 30 days
|  |  |  | Archive Project | Project is either Completed or Canceled, and is now stored in the Project Archive (does not count towards Project Limit)
| Project Details | Will you require any Custom Fields for Projects?
|  |  | Existing Project Metadata vs. Custom Fields | Item | Notes
|  |  | example | Project Name | Naming convention:
|  |  |  | Project Due Date | Project's deadline
|  |  |  | Proposal Title | Custom Field
|  |  |  | RFP Number | Custom Field

## 7. Project Merge Tags
Project Merge Tags (Custom Fields)
Merge tag name | Meaning/definition | Group name | Column1 | Notes